## Start Here
FINISH SCHEDULE TEMPLATE ¦ SPEC SHEET BUILDER
One sheet that answers: can we order this today?
Every finish on a custom home in one place: what the client picked, what it costs against the allowance, when it has to be decided, when it has to be ordered, and whether it is signed. Built by builders for residential jobs. Works in Excel and Google Sheets.
THE ONE RULE
Do not order from a blank. If the model, finish, quantity, supplier, lead time, or approval is missing, the Ready to Order column says so, and it stays amber until it is filled in. Selected is not approved.
THE TABS
Dashboard | Counts, money, and what needs attention, all calculated. Open this first every Monday.
Project | Job info, contract amount, markups, and the four decide-by dates. Fill it in once.
Finish Schedule | The main list. One row per selection. White cells are yours, gray cells calculate: decision due date, actual cost, over/under, order-by date, the Ready to Order check, and flags.
Allowances | Every allowance line rolled up by category: allowance, actual, over/under, billable with markup, and what is not signed yet.
Change Orders | Every change priced and signed before the work, including $0 swaps and overages. Totals feed the revised contract.
Client Sign-Off | A one-page approval sheet. Pick a room at the top and it fills from the Finish Schedule. Print it, get initials and a signature, then put the date in Approved On.
Lists | Rooms, categories, units, and statuses behind every dropdown. Edit to fit how you build.
HOW TO USE IT
Step 1 | Fill in the Project tab: job, client, who can sign changes, contract amount, markups, and the four decide-by dates.
Step 2 | On the Finish Schedule, delete the sample rows (6 to 45), then add one row per selection. Write the item the way the client says it.
Step 3 | Pick a Decide By phase for every row. The Decision Due date fills in and turns red when it passes without approval.
Step 4 | Fill in the spec as you get it: manufacturer, full model number, finish name, qty with a unit, supplier, lead time, and the date it is needed on site.
Step 5 | When the client signs, enter Approved On and Approved By. Use the Client Sign-Off tab to print a room at a time.
Step 6 | Order only rows that say READY. Watch the Flag column and the Dashboard for anything overdue or coming due in two weeks.
COLORS
White cell | Type here.
Gray cell | Calculates. Leave it alone.
READY | Nothing missing. Order it.
Missing / Soon | Something is blank, or the order-by date is within 14 days.
OVERDUE / Over | Past a deadline, or over allowance without a signature.
Ordered | Ordered, received, or installed.
THE SAMPLE JOB
The Lakeshore Residence is made up. Its 40 selections and 5 change orders show every state the sheet can be in: ready, missing a finish, a decision overdue, an order overdue, over allowance and unsigned. Model numbers marked (sample) are illustrative. Dates move with today so the sample always looks live. To start your job, delete Finish Schedule rows 6 to 45 and Change Orders rows 8 to 12 (select the rows, right-click, Delete), then type over the Project tab.
WHERE A SPREADSHEET STOPS
A spreadsheet is a good home for one job and one person. It gets hard when the client, the PM, and three suppliers all need the current version, when you want photos and spec sheets on each line, or when you are running several jobs at once. That is what Spec Sheet Builder does: specsheetbuilder.com
Made by Spec Sheet Builder. Free to use and change for your own jobs.

## Dashboard
Dashboard
Lakeshore Residence (sample) ¦ as of Sep 21, 2026
Gray numbers calculate from the other tabs. Nothing to type here.
SELECTIONS |  | APPROVED |  | READY TO ORDER |  | ORDERED OR LATER
40 |  | 29 |  | 26 |  | 3
lines on the schedule |  | 73% of selections signed |  | nothing missing, order today |  | ordered, received, or installed
NEEDS ATTENTION
DECISIONS OVERDUE |  | ORDERS OVERDUE |  | ORDER WITHIN 2 WEEKS |  | OVERAGE NOT SIGNED
1 |  | 1 |  | 2 |  | 1193
past decide-by, no approval |  | past order-by date |  | order-by date is close |  | over allowance, no approval
MONEY
SELECTIONS TOTAL |  | ALLOWANCE OVER / UNDER |  | SIGNED CHANGE ORDERS |  | REVISED CONTRACT
151677 |  | 4247 |  | 1322.5 |  | 691001.7
actual cost of every line |  | actual minus allowance |  | added to contract |  | projected, if nothing else changes
WHERE EVERY SELECTION STANDS
Status | Lines
Pending | 4
Options Sent | 1
Selected | 6
Approved | 26
Ordered | 3
Received | 0
Installed | 0
On Hold | 0
ALLOWANCE VS ACTUAL, BY CATEGORY
BY ROOM
Room | Selections | Approved | Ready | Actual | Allowance | Over / Under | Unsigned
Kitchen | 9 | 7 | 7 | 47955 | 45460 | 2495 | 93
Pantry | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dining | 0 | 0 | 0 | 0 | 0 | 0 | 0
Great Room | 1 | 1 | 1 | 4200 | 4500 | -300 | 0
Entry / Foyer | 1 | 1 | 1 | 3850 | 3500 | 350 | 0
Mudroom | 0 | 0 | 0 | 0 | 0 | 0 | 0
Laundry | 1 | 1 | 1 | 65 | 0 | 0 | 0
Powder Room | 1 | 0 | 0 | 2100 | 1800 | 300 | 300
Primary Bedroom | 1 | 0 | 0 | 420 | 450 | -30 | 0
Primary Bath | 10 | 7 | 7 | 5814 | 4100 | 255 | 0
Primary Closet | 0 | 0 | 0 | 0 | 0 | 0 | 0
Guest Bath | 2 | 0 | 0 | 1557.5 | 840 | 717.5 | 800
Bedroom 2 | 1 | 0 | 0 | 1512 | 1680 | -168 | 0
Bedroom 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hall Bath | 0 | 0 | 0 | 0 | 0 | 0 | 0
Office | 1 | 1 | 1 | 650 | 0 | 0 | 0
Bonus Room | 0 | 0 | 0 | 0 | 0 | 0 | 0
Garage | 1 | 1 | 1 | 2650 | 0 | 0 | 0
Exterior | 3 | 2 | 0 | 58524 | 0 | 0 | 0
Whole House | 8 | 8 | 7 | 22379.5 | 9000 | 627.5 | 0
Room names come from the Lists tab. Over / Under counts only lines that carry an allowance.

## Project
Project
Fill in the white cells once. Every other tab reads from here.
THE JOB
Project name | Lakeshore Residence (sample) | Shows on every printout.
Address | 1418 Lakeshore Dr, Anytown, NC
Client | Jordan & Casey Miller (sample)
Client email | millers@example.com
Client phone | (555) 010-0142
Who can sign changes | Jordan or Casey Miller | Put this in writing before the first selection. One name avoids 'my spouse never agreed.'
Builder | Your Company Name | Prints at the top of the Client Sign-Off page.
Project manager | Alex Rivera
Contract date | 2026-08-07 | Sample date. Type your real date over it.
Target completion | 2027-04-09 | Sample date. Type your real date over it.
MONEY
Original contract | 685000 | Signed contract amount, before any changes.
Markup on allowance overages | 10% | What your contract says you add when a selection runs over its allowance.
Default change order markup | 15% | Pre-fills each new change order. Override per line.
DECISION DEADLINES
Phase | Decide by | What gets locked at this point
Before you dig | 2026-09-07 | Windows, exterior doors, roofing, siding, anything that changes framing or the foundation.
Before rough-in | 2026-10-12 | Plumbing valves and drains, fixture locations, fireplace, lighting layout, blocking, low voltage.
Before drywall | 2026-11-20 | Tile, cabinets, niches, interior doors, anything that needs backing or exact dimensions.
Before install | 2027-01-09 | Faucets, hardware, lighting fixtures, paint, flooring, mirrors, accessories, shower glass.
Sample dates are relative to today so the sample always looks live. Type real dates over them.
CONTRACT SUMMARY
Original contract | 685000 | From above.
Signed change orders | 1322.5 | Signed only. Over-allowance COs are excluded here so they are not counted twice.
Allowance over/under (billable) | 4679.2 | Net of every allowance line, markup applied to overages. Includes lines not yet signed.
Revised contract (projected) | 691001.7 | What the client should expect to pay if nothing else changes.
Overage not yet signed | 1193 | Money you are carrying on a handshake. Get it signed.

## Finish Schedule
Finish Schedule
Project: Lakeshore Residence (sample) ¦ Client: Jordan & Casey Miller (sample) ¦ Printed Sep 21, 2026
SAMPLE JOB: rows 6 to 45 are a filled-in example with made-up model numbers and dates relative to today. Read them, then delete those rows and start yours. White cells are yours to type in. Gray cells calculate.
WHAT & WHERE |  |  |  |  | DECIDE BY |  | THE SPEC |  |  |  | COST & ALLOWANCE | [5 empty] | ORDERING |  |  |  |  | APPROVAL |  |  | CHECKS |  |  | NOTES
# | Room | Item (client's words) | Location | Category | Decide By | Decision Due | Manufacturer | Model / SKU | Finish | Size | Qty | Unit | Unit Cost | Actual | Allowance | Over / Under | Supplier | Link | Lead Time (days) | Needed On Site | Order By | Status | Approved On | Approved By | Ready to Order? | Flag | Unsigned Overage | Alternates | Notes | helper
1 | Exterior | Windows, whole house | All elevations | Windows & Exterior Doors | Before you dig | 2026-09-07 | Andersen | 400 Series (see window schedule) | White int / White ext | Per schedule | 1 | lot | 38400 | 38400 |  |  | Builders Supply Co | andersenwindows.com | 56 | 2026-10-01 | 2026-08-06 | Ordered | 2026-08-22 | J. Miller | Ordered |  |  |  | Rough openings confirmed with framer.
2 | Entry / Foyer | Front door | Front elevation | Windows & Exterior Doors | Before you dig | 2026-09-07 | Therma-Tru | CCV-205 (sample) | Stained Walnut | 3-0 x 8-0 | 1 | ea | 3850 | 3850 | 3500 | 350 | Builders Supply Co |  | 42 | 2026-10-21 | 2026-09-09 | Approved | 2026-09-01 | J. Miller | READY | ORDER OVERDUE |  |  | Approved but not ordered yet. Lead time says it is already late.
3 | Exterior | Roof shingles | Main roof | Roofing | Before you dig | 2026-09-07 | GAF | Timberline HDZ | Charcoal |  | 32 | sq | 142 | 4544 |  |  | ABC Roofing Supply |  | 7 | 2026-09-26 | 2026-09-19 | Ordered | 2026-08-27 | C. Miller | Ordered
4 | Exterior | Lap siding | All elevations | Siding & Exterior | Before you dig | 2026-09-07 | James Hardie | HardiePlank Lap 8.25 in |  |  | 38 | sq | 410 | 15580 |  |  | Builders Supply Co |  | 28 | 2026-12-20 | 2026-11-22 | Selected |  |  | Missing: finish, approval | DECISION OVERDUE |  |  | Color not picked. Blocks the siding order.
5 | Garage | Garage door | 2-car bay | Windows & Exterior Doors | Before drywall | 2026-11-20 | Clopay | Gallery GD-16 (sample) | Black | 16 x 8 | 1 | ea | 2650 | 2650 |  |  | Overhead Door Pros |  | 35 | 2026-12-30 | 2026-11-25 | Approved | 2026-09-11 | J. Miller | READY
6 | Kitchen | Kitchen cabinets | Perimeter + island | Cabinetry | Before rough-in | 2026-10-12 | Local cabinet shop | Shaker, full overlay | SW 7005 perimeter / navy island |  | 1 | lot | 28500 | 28500 | 28000 | 500 | Carolina Cabinetry |  | 70 | 2026-12-05 | 2026-09-26 | Approved | 2026-09-14 | C. Miller | READY | ORDER SOON |  |  | Shop drawings signed. Order within the week.
7 | Primary Bath | Linear shower drain | Shower, back wall | Plumbing Fixtures | Before rough-in | 2026-10-12 | Schluter | KERDI-LINE 36 in (sample) | Brushed Stainless | 36 in | 1 | ea | 289 | 289 |  |  | Tile Outlet |  | 10 | 2026-10-21 | 2026-10-11 | Approved | 2026-09-16 | J. Miller | READY |  |  |  |  | 1
8 | Great Room | Gas fireplace insert | TV wall | Fireplace | Before rough-in | 2026-10-12 | Heat & Glo | FP-42 (sample) | Black | 42 in | 1 | ea | 4200 | 4200 | 4500 | -300 | Hearth & Home |  | 30 | 2026-11-10 | 2026-10-11 | Approved | 2026-09-09 | J. Miller | READY |  |  |  | Gas line and venting on rough-in plan.
9 | Kitchen | Appliance package | Kitchen | Appliances | Before rough-in | 2026-10-12 | Cafe | Range, hood, fridge, DW, micro (sample) | Matte White / Brushed Bronze |  | 1 | lot | 10850 | 10850 | 9500 | 1350 | Appliance Depot |  | 45 | 2026-11-15 | 2026-10-01 | Approved | 2026-09-18 | C. Miller | READY | ORDER SOON |  |  | Over allowance, signed. Cutout specs to cabinet shop.
10 | Kitchen | Kitchen faucet | Sink | Plumbing Fixtures | Before install | 2027-01-09 | Delta | 9178-AR-DST (sample) | Arctic Stainless |  | 1 | ea | 389 | 389 | 450 | -61 | Plumbing Supply Co |  | 10 | 2027-01-04 | 2026-12-25 | Approved | 2026-09-13 | J. Miller | READY
11 | Kitchen | Kitchen sink | Island | Plumbing Fixtures | Before drywall | 2026-11-20 | Kohler | K-6488 (sample) | White | 36 in | 1 | ea | 540 | 540 | 500 | 40 | Plumbing Supply Co |  | 21 | 2026-11-30 | 2026-11-09 | Approved | 2026-09-13 | J. Miller | READY |  |  |  | Template needs the sink on site.
12 | Guest Bath | The gold faucet | Vanity | Plumbing Fixtures | Before install | 2027-01-09 | Brizo | 65050LF-GL (sample) | Luxe Gold |  | 1 | ea | 1200 | 1200 | 400 | 800 | Plumbing Supply Co |  | 21 | 2027-01-04 | 2026-12-14 | Selected |  |  | Missing: approval |  | 800 | Kohler K-14406-4-CP or Moen TS32104, client approval required | $800 over allowance. Change order drafted, not signed.
13 | Primary Bath | Vanity faucets | Double vanity | Plumbing Fixtures | Before install | 2027-01-09 | Moen | 6192BG (sample) | Brushed Gold |  | 2 | ea | 365 | 730 | 800 | -70 | Plumbing Supply Co |  | 14 | 2027-01-04 | 2026-12-21 | Approved | 2026-09-15 | C. Miller | READY |  |  |  |  | 2
14 | Primary Bath | Shower valve and trim | Shower | Plumbing Fixtures | Before rough-in | 2026-10-12 | Kohler | K-TS73060-4 (sample) | Vibrant Brushed Moderne Brass |  | 1 | set | 1180 | 1180 | 900 | 280 | Plumbing Supply Co |  | 14 | 2026-10-29 | 2026-10-15 | Approved | 2026-09-12 | J. Miller | READY |  |  |  | Valve body needed at rough-in, trim at install. | 3
15 | Whole House | Toilets | All baths | Plumbing Fixtures | Before install | 2027-01-09 | TOTO | Drake II (sample) | Cotton White |  | 4 | ea | 395 | 1580 | 1600 | -20 | Plumbing Supply Co | hudsonvalleylighting.com | 14 | 2027-01-04 | 2026-12-21 | Approved | 2026-09-15 | J. Miller | READY
16 | Laundry | Washer box | Laundry wall | Plumbing Fixtures | Before rough-in | 2026-10-12 | Oatey | Fire-rated box (sample) | N/A |  | 1 | ea | 65 | 65 |  |  | Plumbing Supply Co |  | 3 | 2026-10-11 | 2026-10-08 | Approved | 2026-09-11 | J. Miller | READY
17 | Whole House | Recessed lights | Per lighting plan | Lighting | Before rough-in | 2026-10-12 | Halo | 6 in LED (sample) | 3000K, white trim | 6 in | 42 | ea | 28 | 1176 |  |  | City Electric |  | 7 | 2026-10-16 | 2026-10-09 | Approved | 2026-09-11 | C. Miller | READY |  |  |  | Count walked with client on the plan.
18 | Primary Bedroom | Ceiling fan | Center of room | Lighting | Before rough-in | 2026-10-12 | Minka Aire |  |  | 52 in | 1 | ea | 420 | 420 | 450 | -30 | City Electric |  | 10 | 2027-01-04 | 2026-12-25 | Pending |  |  | Missing: model, finish, approval |  |  |  | Fan-rated box goes in at rough-in either way.
19 | Kitchen | Pendant over sink | Sink window | Lighting | Before install | 2027-01-09 | Visual Comfort | PL-110 (sample) | Aged Brass |  | 1 | ea | 275 | 275 | 350 | -75 | Lighting Gallery |  | 21 | 2026-12-30 | 2026-12-09 | Approved | 2026-09-17 | C. Miller | READY
20 | Kitchen | Island pendants | Island | Lighting | Before install | 2027-01-09 | Hudson Valley |  |  |  | 3 | ea | 310 | 930 | 900 | 30 | Lighting Gallery |  | 28 | 2026-12-30 | 2026-12-02 | Options Sent |  |  | Missing: model, finish, approval |  | 30 | Two options sent Sept. Client leaning toward the larger one.
21 | Whole House | Switches and outlets | Throughout | Electrical Devices | Before rough-in | 2026-10-12 | Lutron / Leviton | Decora (sample) | White |  | 1 | lot | 1450 | 1450 |  |  | City Electric |  | 5 | 2026-11-25 | 2026-11-20 | Approved | 2026-09-11 | J. Miller | READY
22 | Primary Bath | Shower niche | Shower, side wall | Tile | Before drywall | 2026-11-20 | Schluter | KERDI-BOARD-SN (sample) | N/A | 12 x 28 | 1 | ea | 185 | 185 |  |  | Tile Outlet |  | 7 | 2026-11-05 | 2026-10-29 | Approved | 2026-09-15 | J. Miller | READY |  |  |  | Height set to clear the valve. | 4
23 | Primary Bath | Blocking, grab bar and glass | Shower + toilet | Other | Before drywall | 2026-11-20 | Framing crew | 2x10 blocking | N/A |  | 1 | lot | 120 | 120 |  |  | Framing crew |  | 1 | 2026-10-31 | 2026-10-30 | Approved | 2026-09-15 | J. Miller | READY |  |  |  | Photograph before drywall. | 5
24 | Powder Room | Floating vanity | Powder room | Cabinetry | Before drywall | 2026-11-20 | Local cabinet shop | Floating, 1 drawer | Walnut | 36 in | 1 | ea | 2100 | 2100 | 1800 | 300 | Carolina Cabinetry |  | 42 | 2026-12-30 | 2026-11-18 | Selected |  |  | Missing: approval |  | 300 |  | $300 over. Needs signature.
25 | Office | Low voltage and data | Office + great room | Electrical Devices | Before rough-in | 2026-10-12 | Local LV sub | Cat6 + coax (sample) | N/A |  | 1 | lot | 650 | 650 |  |  | Local LV sub |  | 3 | 2026-10-16 | 2026-10-13 | Approved | 2026-09-11 | C. Miller | READY
26 | Primary Bath | Floor tile | Bath floor | Tile | Before drywall | 2026-11-20 | Daltile | 12x24 porcelain (sample) | Matte Ash | 12 x 24 | 120 | sf | 9.5 | 1140 | 960 | 180 | Tile Outlet |  | 21 | 2026-11-30 | 2026-11-09 | Approved | 2026-09-16 | J. Miller | READY |  |  |  | Add 10% waste to the order, not the allowance math. | 6
27 | Primary Bath | Shower wall tile | Shower walls | Tile | Before drywall | 2026-11-20 | Daltile | 3x12 ceramic (sample) | Gloss White | 3 x 12 | 180 | sf | 7.25 | 1305 | 1440 | -135 | Tile Outlet |  | 21 | 2026-11-30 | 2026-11-09 | Approved | 2026-09-16 | J. Miller | READY |  |  |  |  | 7
28 | Kitchen | Backsplash | Range wall + sink wall | Tile | Before install | 2027-01-09 | Bedrosians | Zellige 4x4 (sample) | Sage | 4 x 4 | 38 | sf | 14 | 532 | 380 | 152 | Tile Outlet |  | 21 | 2026-12-25 | 2026-12-04 | Approved | 2026-09-17 | C. Miller | READY
29 | Guest Bath | Floor tile | Bath floor | Tile | Before drywall | 2026-11-20 | Daltile |  |  |  | 55 | sf | 6.5 | 357.5 | 440 | -82.5 | Tile Outlet |  | 21 | 2026-12-02 | 2026-11-11 | Pending |  |  | Missing: model, finish, approval |  |  |  | Samples dropped off. Waiting on client.
30 | Kitchen | Quartz countertops | Perimeter + island | Countertops | Before install | 2027-01-09 | Cambria | Brittanicca (sample) | Polished, 3 cm |  | 62 | sf | 88 | 5456 | 4960 | 496 | Stone Fabricators |  | 14 | 2026-12-25 | 2026-12-11 | Approved | 2026-09-17 | J. Miller | READY |  |  |  | Template after cabinets set.
31 | Kitchen | Cabinet pulls | Kitchen + island | Cabinet Hardware | Before install | 2027-01-09 | Top Knobs | TK-3223 (sample) | Honey Bronze | 6-5/16 in | 42 | ea | 11.5 | 483 | 420 | 63 | Hardware Source |  | 14 | 2026-12-30 | 2026-12-16 | Selected |  |  | Missing: approval |  | 63
32 | Whole House | Door levers | Interior doors | Door Hardware | Before install | 2027-01-09 | Emtek | 5000 series (sample) | Matte Black |  | 22 | ea | 68 | 1496 |  |  | Hardware Source |  | 28 | 2026-12-30 | 2026-12-02 | Approved | 2026-09-17 | C. Miller | READY
33 | Whole House | Interior doors | Throughout | Interior Doors | Before drywall | 2026-11-20 | Masonite | 2-panel shaker (sample) | Primed | Per schedule | 22 | ea | 245 | 5390 |  |  | Builders Supply Co |  | 28 | 2026-12-10 | 2026-11-12 | Approved | 2026-09-11 | J. Miller | READY
34 | Whole House | Wall paint | Walls | Paint | Before install | 2027-01-09 | Sherwin-Williams | SW 7036 Accessible Beige | Eggshell |  | 32 | gal | 72 | 2304 |  |  | Sherwin-Williams store |  | 2 | 2026-12-20 | 2026-12-18 | Approved | 2026-09-18 | C. Miller | READY
35 | Whole House | Trim paint | Trim and doors | Paint | Before install | 2027-01-09 | Sherwin-Williams | SW 7005 Pure White | Semi-Gloss |  | 12 | gal | 78 | 936 |  |  | Sherwin-Williams store |  | 2 | 2026-12-20 | 2026-12-18 | Approved | 2026-09-18 | C. Miller | READY
36 | Whole House | LVP flooring | Main level | Flooring | Before install | 2027-01-09 | COREtec | Plus 7 in (sample) | Natural Oak |  | 1850 | sf | 4.35 | 8047.5 | 7400 | 647.5 | Floor Center |  | 21 | 2026-12-15 | 2026-11-24 | Ordered | 2026-09-01 | J. Miller | Ordered |  |  |  | Acclimate on site 72 hours.
37 | Bedroom 2 | Carpet | Bedrooms 2 and 3 | Flooring | Before install | 2027-01-09 | Shaw |  |  |  | 420 | sf | 3.6 | 1512 | 1680 | -168 | Floor Center |  | 14 | 2027-01-04 | 2026-12-21 | Pending |  |  | Missing: model, finish, approval
38 | Primary Bath | Shower glass | Shower | Shower Glass | Before install | 2027-01-09 | Local glass shop |  |  |  | 1 | ea |  |  |  |  | Local glass shop |  | 14 | 2027-01-09 | 2026-12-26 | Pending |  |  | Missing: model, finish, approval |  |  |  | Measure after tile. Price comes then. | 8
39 | Primary Bath | Mirrors | Over vanity | Mirrors & Accessories | Before install | 2027-01-09 | Kohler | Essential 24x36 (sample) | Brushed Gold frame | 24 x 36 | 2 | ea | 240 | 480 |  |  | Plumbing Supply Co |  | 14 | 2027-01-04 | 2026-12-21 | Selected |  |  | Missing: approval |  |  |  |  | 9
40 | Primary Bath | Towel bars and accessories | Bath | Mirrors & Accessories | Before install | 2027-01-09 | Moen | Align set (sample) | Brushed Gold |  | 1 | set | 385 | 385 |  |  | Plumbing Supply Co |  | 14 | 2027-01-04 | 2026-12-21 | Selected |  |  | Missing: approval |  |  |  |  | 10
Formulas:
Decision Due = IF([DECIDE BY]="","",IFERROR(IF(INDEX(Project!$C24:C27,MATCH([DECIDE BY],Project!$B24:B27,0))="","",INDEX(Project!$C24:C27,MATCH([DECIDE BY],Project!$B24:B27,0))),""))
Order By = IF(OR([Needed On Site]="",[Lead Time (days)]=""),"",[Needed On Site]-[Lead Time (days)])
Flag = IF([Item (client's words)]="","",IF(OR([APPROVAL]="Ordered",[APPROVAL]="Received",[APPROVAL]="Installed"),"",IF(AND([Decision Due]<>"",[Approved On]="",[Decision Due]<TODAY()),"DECISION OVERDUE",IF([Order By]="","",IF([Order By]<TODAY(),"ORDER OVERDUE",IF([Order By]-TODAY()<=14,"ORDER SOON",""))))))
Note on C5: Write it the way the client says it: 'the gold faucet in the guest bath.' Nobody should need a decoder.
Note on F5: Pick the phase this has to be decided by. The date comes from the Project tab.
Note on I5: Full model number or SKU. 'Moen brushed' is not a model. Do not order from a blank.
Note on J5: Use the manufacturer's finish name and code. 'Gold' is three different golds at three suppliers. No finish on this item? Type N/A so the check knows it is on purpose.
Note on L5: Quantity with a unit. 120 sf is not the same order as 120 boxes.
Note on N5: Your cost per unit. Actual = Qty x Unit Cost.
Note on P5: The allowance for this line from your contract. Leave blank if the line is not an allowance item.
Note on T5: Days from order to delivery, from the supplier. Ask, do not guess.
Note on U5: The day it has to be on site. Order By = this date minus lead time.
Note on W5: Selected is not Approved. Selected means the client liked it. Approved means it is signed.
Note on X5: Date the client signed off. Blank here means you do not have approval.
Note on Z5: The pre-order check: model, finish, qty, supplier, lead time, approval. READY means you can order this today.
Note on AA5: DECISION OVERDUE: past the decide-by date with no approval. ORDER OVERDUE: past the order-by date. ORDER SOON: within 14 days.
Note on AB5: Over allowance and not yet approved. Sign overages the day they are chosen.
Note on AC5: Name real alternates: 'Kohler K-14406-4-CP or Moen TS32104, client approval required.' Avoid 'or equal.'

## Allowances
Allowances
Every allowance line on the Finish Schedule, rolled up by category. Rename the white category cells to match your contract.
Sign overages the day they are chosen, not at the final invoice. The Unsigned column is money you are carrying on a handshake.
Category | Allowance | Actual | Over / Under | % Over | Billable (with markup) | Lines | Approved | Unsigned Overage | Status
Plumbing Fixtures | 4650 | 5619 | 969 | 20.84% | 1065.9 | 6 | 5 | 800 | Unsigned overage
Tile | 3220 | 3334.5 | 114.5 | 3.556% | 125.95 | 4 | 3 | 0 | Over, signed
Lighting | 1700 | 1625 | -75 | -4.412% | -75 | 3 | 1 | 30 | Unsigned overage
Cabinetry | 29800 | 30600 | 800 | 2.685% | 880 | 2 | 1 | 300 | Unsigned overage
Countertops | 4960 | 5456 | 496 | 10% | 545.6 | 1 | 1 | 0 | Over, signed
Appliances | 9500 | 10850 | 1350 | 14.21% | 1485 | 1 | 1 | 0 | Over, signed
Flooring | 9080 | 9559.5 | 479.5 | 5.281% | 527.45 | 2 | 1 | 0 | Over, signed
Cabinet Hardware | 420 | 483 | 63 | 15% | 69.3 | 1 | 0 | 63 | Unsigned overage
All other categories | 8000 | 8050 | 50 | 0.625% | 55 | 2 | 2 | 0 | Over, signed
Total | 71330 | 75577 | 4247 | 5.954% | 4679.2 | 22 | 15 | 1193
WHAT THIS MEANS
Net over / under | 4247 | Actual minus allowance across every allowance line.
Markup on overages | 10% | From the Project tab.
Billable to client | 4679.2 | Overages carry markup. Credits come back at cost.
Not yet signed | 1193 | Chase these first.
Line-level detail lives on the Finish Schedule: filter the Allowance column to non-blank. 'All other categories' catches allowance lines whose category is not listed above.

## Change Orders
Change Orders
Every change, priced and signed before the work. Swaps, add-ons, surprises, and overages all go here, even the $0 ones.
| SIGNED CHANGES (ADDED TO CONTRACT) |  |  | DAYS ADDED (SIGNED) |  |  | WAITING ON THE CLIENT |  |  | OPEN CHANGE ORDERS
| 1322.5 |  |  | 3 |  |  | 1363 |  |  | 2
Over-allowance COs are tracked here for the signature but left out of the Signed total, because the Allowances tab already counts them. Void COs count nowhere.
CO # | Date | Type | Room | What changed | Was | Now | Cost | Markup | Price to Client | Days | Requested By | Status | Signed By | Date Signed | Notes
CO-01 | 2026-08-22 | Added scope | Mudroom | Add window over mudroom bench | No window | Andersen 400 Series 2-0 x 3-0 (sample) | 1150 | 15% | 1322.5 | 3 | Client | Signed | J. Miller | 2026-08-24 | Header resized. Framer notified.
CO-02 | 2026-09-03 | Unforeseen | Primary Bath | Floor tile discontinued, replaced | Original 12x24 tile (discontinued) | Daltile 12x24 Matte Ash, same price, client picked | 0 | 15% | 0 | 0 | Supplier | Signed | J. Miller | 2026-09-04 | $0, still signed so it is on paper.
CO-03 | 2026-09-15 | Client swap | Kitchen | Farmhouse sink to workstation sink | Kohler K-6488 (sample) | Workstation sink with accessories (sample) | 420 | 15% | 483 | 2 | Client | Sent |  |  | Countertop template waits on this.
CO-04 | 2026-09-19 | Over allowance | Guest Bath | Guest bath faucet over allowance | $400 allowance | Brizo Luxe Gold, $1,200 (sample) | 800 | 10% | 880 | 0 | Client | Draft |  |  | Allowance markup rate. Counted on the Allowances tab, not in Signed total.
CO-05 | 2026-09-09 | Added scope | Pantry | Add outlet for coffee station | No outlet | Duplex outlet at counter height | 0 | 15% | 0 | 0 | Client | Signed | C. Miller | 2026-09-10 | No charge, goodwill. Signed anyway.

## Client Sign-Off
Your Company Name
Selections for Approval
| Project | Lakeshore Residence (sample)
| Address | 1418 Lakeshore Dr, Anytown, NC
| Client | Jordan & Casey Miller (sample)
| Room | Primary Bath |  |  | <- pick a room
| Prepared | September 21, 2026
Please review each line. Initial the lines you approve. Anything over its allowance is shown in the Over/Under column and will be billed as a change.
# | Location | Item | Make / Model | Finish | Qty | Allowance | Price | Over / Under | Initials
1 | Shower, back wall | Linear shower drain | Schluter KERDI-LINE 36 in (sample) | Brushed Stainless | 1 ea |  | 289
2 | Double vanity | Vanity faucets | Moen 6192BG (sample) | Brushed Gold | 2 ea | 800 | 730 | -70
3 | Shower | Shower valve and trim | Kohler K-TS73060-4 (sample) | Vibrant Brushed Moderne Brass | 1 set | 900 | 1180 | 280
4 | Shower, side wall | Shower niche | Schluter KERDI-BOARD-SN (sample) | N/A | 1 ea |  | 185
5 | Shower + toilet | Blocking, grab bar and glass | Framing crew 2x10 blocking | N/A | 1 lot |  | 120
6 | Bath floor | Floor tile | Daltile 12x24 porcelain (sample) | Matte Ash | 120 sf | 960 | 1140 | 180
7 | Shower walls | Shower wall tile | Daltile 3x12 ceramic (sample) | Gloss White | 180 sf | 1440 | 1305 | -135
8 | Shower | Shower glass | Local glass shop |  | 1 ea
9 | Over vanity | Mirrors | Kohler Essential 24x36 (sample) | Brushed Gold frame | 2 ea |  | 480
10 | Bath | Towel bars and accessories | Moen Align set (sample) | Brushed Gold | 1 set |  | 385
[5 empty] | Totals | 4100 | 5814 | 255
Selections in this room that are over their allowance, not yet approved: | [6 empty] | 0
By signing, I approve the selections above, including any amount over allowance, and understand changes after this date may affect cost and schedule and will be handled by written change order.
Client signature Date |  |  |  |  | Builder signature Date
Prepared with the Finish Schedule Template from Spec Sheet Builder. Lakeshore Residence (sample)

## Lists
Lists
Edit these to match how you build. Dropdowns on every tab read from here. Add to the blank spares; do not insert rows above row 4.
Decide-By Phases | Rooms | Categories | Units | Statuses | CO Types | CO Statuses
Before you dig | Kitchen | Flooring | ea | Pending | Client swap | Draft
Before rough-in | Pantry | Tile | sf | Options Sent | Over allowance | Sent
Before drywall | Dining | Plumbing Fixtures | lf | Selected | Added scope | Signed
Before install | Great Room | Lighting | sy | Approved | Unforeseen | Void
| Entry / Foyer | Cabinetry | sq | Ordered
| Mudroom | Countertops | set | Received
Phases are fixed: their dates live on the Project tab. | Laundry | Cabinet Hardware | pr | Installed
| Powder Room | Appliances | gal | On Hold
| Primary Bedroom | Door Hardware | box
| Primary Bath | Interior Doors | lot | Statuses drive colors and counts. Rename with care.
| Primary Closet | Trim & Millwork
| Guest Bath | Paint
| Bedroom 2 | Mirrors & Accessories
| Bedroom 3 | Shower Glass
| Hall Bath | Windows & Exterior Doors
| Office | Roofing
| Bonus Room | Siding & Exterior
| Garage | Fireplace
| Exterior | Electrical Devices
| Whole House | Other